## Slide 1: Ashland Public Schools School Start Time Process
April 2014 - September 2017

## Slide 2: Timeline of Process
April 2014 - Initial Request to Create School Start Time Committee (SSTC)
September 2014 - SSTC created
1 Parent Site Council Member Each From Warren, Mindess, AMS, and AHS –
1 Teacher Representative from Warren, Mindess, AMS, and AHS
1 School Committee Member
1 Administrator from Warren, Mindess, AMS, and AHS
1 Administrator from Central Office
1 AHS Athletic Director
1 AHS Student as elected by AHS Student Government
November/December 2014 - Community Forums
SSTC Discussion Phases
Multi-Layered
February 2016 - School Committee Recommendation - SC Official Vote on Modifying Times
September 2017 - Start Time Begins

## Slide 3: Important Steps
Mission Development
To review the current research on school start times, explore relevant factors and policies of comparable districts, and gather community input to make recommendations for start times that are feasible and appropriate for Ashland. The success and well-being of all students in our district will be at the forefront of our work.
Discussion Phases
Phase I: Review of Research, Informational Gathering and Dissemination (Completed by January 2015)
Committee Formed to Review Research and Disseminate Information to Community
  Meetings
  Community Forums
  Student Focus Groups
  FAQ Sheet Developed Based on Research
  Surveys of (Students, Educators, Parents)
    Research
    Perceived and Real Barriers
    Analysis of Survey
  Analysis of Findings to School Committee
    Recommendation to either pursue a time change or not
  Recommendation of Potential Time Change
    What are some options to be discussed?

## Slide 4
Phase II: Identification of Potential Barriers and Solutions – (Final Report to SC May of 2015/Actual January 2016)
Committee Formed in February 2015
Based on Recommended Time Change – Research of Costs and Impact
  Bussing
  Day Care
  Athletic Concerns
  Survey of Perceived Impact
Phase III: Recommendation to School Committee on Time Change – (May 2015/Actual February 2016)
School Committee votes on time change if recommended
Phase IV: Potential Implementation of School Start Time (School Year 2016-2017- Approved for 2017-18)
Education of the Ashland community on changes – (SY 2015-2016)
Budget Impact ( December 2016)
Full Implementation August 2016
Creation of a Lib Guide http://ashlandhs.libguides.com/StartTimes
Community Forums
Athletic Director Meetings
Tri-Valley League
Newspaper Articles
School Committee Updates
FAQ Page